## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | As a candidate, I want to register in the ExamGuard system so that I can access the online examination securely. | MUST HAVE | Flask, SQLite | Revu Siri Harshini | 3-Completed
S1 | S1 | US-002 | As a candidate, I want to log in securely using my application ID and password so that I can access my examination. | MUST HAVE | Registration, SQLite, Password Hashing | Revu Siri Harshini | 3-Completed
S1 | S1 | US-003 | As a candidate, I want my identity to be verified using face detection before the examination so that unauthorized users cannot take the exam. | MUST HAVE | OpenCV, MediaPipe, Camera Module | Revu Siri Harshini | 3-Completed
S1 | S1 | US-004 | As a candidate, I want the system to monitor my activities during the examination so that suspicious behavior can be identified. | MUST HAVE | Face Verification, Proctoring Module | Revu Siri Harshini | 3-Completed
S2 | S2 | US-005 | As a system, I want to detect and record suspicious events during an examination so that proctoring activity can be reviewed later. | MUST HAVE | Proctoring Module, SQLite | Revu Siri Harshini | 3-Completed
S2 | S2 | US-006 | As a candidate, I want to receive warnings when suspicious activity is detected during my examination. | MUST HAVE | Event Detection | Revu Siri Harshini | 3-Completed
S2 | S2 | US-007 | As a system, I want to calculate examination integrity scores based on detected events so that exam integrity can be evaluated. | MUST HAVE | Event Logs, Integrity Module | Revu Siri Harshini | 3-Completed
S3 | S3 | US-008 | As a system, I want to classify candidates according to their examination risk level based on integrity data. | SHOULD HAVE | Integrity Scoring, Machine Learning | Revu Siri Harshini | 3-Completed
S3 | S3 | US-009 | As an administrator, I want to view candidate examination analytics so that examination integrity can be analyzed. | SHOULD HAVE | Integrity Scoring, Analytics | Revu Siri Harshini | 3-Completed
S4 | S4 | US-010 | As an administrator, I want to view examination monitoring information through a dashboard so that I can monitor candidate activity. | MUST HAVE | Flask, SQLite, Streamlit | Revu Siri Harshini | 3-Completed
S4 | S4 | US-011 | As an administrator, I want to view event logs, integrity scores, risk levels and analytics in the dashboard so that I can analyze examination integrity. | MUST HAVE | Streamlit, Pandas, SQLite | Revu Siri Harshini | 3-Completed
S4 | S4 | US-012 | As an administrator, I want to export examination and proctoring data so that the information can be used for further analysis. | SHOULD HAVE | Streamlit Dashboard, Pandas | Revu Siri Harshini | 3-Completed
S5 | S5 | US-013 | As an administrator, I want AI-assisted examination integrity reports so that important examination findings can be summarized. | SHOULD HAVE | LangChain, OpenAI, Integrity Data | Revu Siri Harshini | 3-Completed
S5 | S5 | US-014 | As a developer, I want to perform end-to-end testing of the ExamGuard system so that the complete examination workflow can be verified. | MUST HAVE | Completed Modules, Test Environment | Revu Siri Harshini | 3-Completed
S5 | S5 | US-015 | As a developer, I want to prepare the ExamGuard application for deployment so that the system can be made available online. | SHOULD HAVE | GitHub, Vercel | Revu Siri Harshini | 2-In Progress
S5 | S5 | US-016 | As an administrator, I want to review examination reports and exported data so that proctoring results can be evaluated. | SHOULD HAVE | Reports, Data Export | Revu Siri Harshini | 3-Completed
S5 | S5 | US-017 | As a developer, I want to document the ExamGuard system and its testing results so that the project can be maintained and demonstrated. | SHOULD HAVE | Completed Modules, Test Results | Revu Siri Harshini | 3-Completed

## Sprint Backlog
US ID | Task ID | Task Description | Start Date | Completion Date | Team Member | Activity | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-001 | T1 | Implement candidate registration and login with application ID and password | 2026-01-09 | 2026-02-09 | Revu Siri Harshini | Coding | 3-Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T2 | Implement secure password hashing and candidate authentication | 2026-03-09 | 2026-04-09 | Revu Siri Harshini | Coding | 3-Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T3 | Implement face verification using OpenCV and MediaPipe | 2026-05-09 | 2026-06-09 | Revu Siri Harshini | Coding | 3-Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T4 | Implement examination activity monitoring and camera-based proctoring | 2026-07-09 | 2026-08-09 | Revu Siri Harshini | Coding | 3-Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T5 | Implement suspicious event detection and event logging | 2026-09-09 | 9/9/202610/9/2026 | Revu Siri Harshini | Coding | 3-Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T6 | Implement candidate warning system for suspicious activities | 2026-11-09 | 2026-11-09 | Revu Siri Harshini | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T7 | Implement examination integrity score calculation | 2026-12-09 | 2026-12-09 | Revu Siri Harshini | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T8 | Implement candidate risk classification using machine learning | 13-09-2026 | 14-09-2026 | Revu Siri Harshini | Coding | 3-Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T9 | Implement candidate examination analytics | 15-09-2026 | 15-09-2026 | Revu Siri Harshini | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T10 | Develop administrator monitoring dashboard using Streamlit | 16-09-2026 | 16-09-2026 | Revu Siri Harshini | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T11 | Display event logs, integrity scores, risk levels and analytics in the administrator dashboard | 16-09-2026 | 16-09-2026 | Revu Siri Harshini | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T12 | Implement examination and proctoring data export | 16-09-2026 | 16-09-2026 | Revu Siri Harshini | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | T13 | Implement AI-assisted examination integrity report generation | 17-09-2026 | 17-09-2026 | Revu Siri Harshini | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T14 | Perform end-to-end testing of the complete examination workflow | 17-09-2026 | 17-09-2026 | Revu Siri Harshini | Testing | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T15 | Prepare ExamGuard application for online deployment | 17-09-2026 | 18-09-2026 | Revu Siri Harshini | Deployment | 2-In Progress | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | T16 | Review examination reports and exported proctoring data | 18-09-2026 | 18-09-2026 | Revu Siri Harshini | Review | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | T17 | Document the ExamGuard system and testing results | 18-09-2026 | 18-09-2026 | Revu Siri Harshini | Documentation | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand-up Meeting
Sl No. | Sprint | Day | Impediments | Action Taken
1 | S1 | 2026-01-09 | Understanding project requirements and setting up the development environment | Reviewed requirements and configured the Flask, SQLite and Python environment
2 | S1 | 2026-03-09 | Initial authentication and registration implementation | Implemented candidate registration and secure login functionality
3 | S2 | 2026-05-09 | Face verification and camera integration required testing | Implemented OpenCV and MediaPipe based face verification and tested camera functionality
4 | S2 | 2026-08-09 | Suspicious event detection required validation during examination | Implemented event detection, event logging and candidate warning functionality
5 | S3 | 2026-12-09 | Integrity scoring and risk classification needed validation | Implemented integrity score calculation and candidate risk classification
6 | S3 | 14-09-2026 | Analytics and dashboard data needed to be verified | Implemented candidate analytics and connected examination data with the dashboard
7 | S4 | 15-09-2026 | Administrator dashboard required validation of event and integrity data | Implemented Streamlit dashboard with event logs, integrity scores, risk levels and analytics
8 | S4 | 16-09-2026 | Data export functionality needed testing | Implemented and tested examination and proctoring data export
9 | S5 | 17-09-2026 | AI report generation and complete workflow required final testing | Implemented AI-assisted integrity reports and performed end-to-end testing
10 | S5 | 18-09-2026 | Deployment and documentation required final review | Prepared the application for deployment and completed project documentation

## Retrospection
SL | Sprint | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2026-01-09 | 2026-04-09 | Revu Siri Harshini | Setting up the project and implementing registration and login | Delaying integration testing | Continue systematic development and testing | Complete authentication testing before moving to the next module
2 | S2 | 2026-05-09 | 2026-08-09 | Revu Siri Harshini | Implementing face verification and suspicious event detection | Waiting until all proctoring features were integrated | Continue testing camera and event detection functionality | Test each proctoring feature with different scenarios
3 | S3 | 2026-09-09 | 2026-12-09 | Revu Siri Harshini | Implementing integrity scoring, risk classification and analytics | Initial dashboard data validation issues | Continue validating integrity and analytics results | Verify dashboard data against database records
4 | S4 | 13-09-2026 | 16-09-2026 | Revu Siri Harshini | Developing the administrator dashboard and data export | Dependency compatibility issues during testing | Continue dashboard testing and export validation | Use compatible package versions and maintain separate environments where required
5 | S5 | 17-09-2026 | 18-09-2026 | Revu Siri Harshini | Completing AI reports, end-to-end testing and documentation | Deployment dependency and bundle-size limitations | Continue deployment preparation and final documentation | Review deployment requirements and finalize project deliverables