## Defects
SI No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Revu Siri Harshini | 2026-02-09 | Invalid candidate credentials were not handled correctly during login testing | S1 | Revu Siri Harshini | Functional | Added proper validation and error handling for invalid credentials | 2026-02-09 | Closed | Login validation tested successfully
2 | Revu Siri Harshini | 2026-06-09 | Camera/video feed could become unavailable during camera processing | S2 | Revu Siri Harshini | Functional | Added error handling for camera and video feed processing | 2026-06-09 | Closed | Camera functionality tested successfully
3 | Revu Siri Harshini | 2026-08-09 | Suspicious events were not handled correctly in some examination test scenarios | S2 | Revu Siri Harshini | Functional | Corrected suspicious event detection and event logging logic | 2026-08-09 | Closed | Event detection and logging verified
4 | Revu Siri Harshini | 2026-12-09 | Dashboard displayed an incorrect or unknown course value during testing | S3 | Revu Siri Harshini | Data | Corrected course data handling and dashboard display logic | 2026-12-09 | Closed | Dashboard data verified
5 | Revu Siri Harshini | 14/09/2026 | Dependency compatibility issues occurred between the dashboard and AI/ML environment | S4 | Revu Siri Harshini | Environment | Separated dashboard environment and aligned compatible package versions | 14/09/2026 | Closed | Flask and Streamlit environments tested separately
6 | Revu Siri Harshini | 16/09/2026 | Deployment dependency resolution failed because of incompatible package versions | S5 | Revu Siri Harshini | Environment | Updated dependency versions to compatible releases and verified installation | 16/09/2026 | Closed | Dependencies installed successfully
7 | Revu Siri Harshini | 17/09/2026 | Vercel deployment exceeded the serverless function bundle-size limit because of large AI/ML dependencies | S5 | Revu Siri Harshini | Deployment | Identified the deployment limitation and reviewed the application deployment requirements | 17/09/2026 | Open | Deployment limitation remains under review

## Sheet2
Type Of Defect
Logical
User Interface
Maintainability
Standards
Others